## Sheet1
Index | Activity Description | Required Predecessor | Duration (weeks) | Internal Deadline | Deadline
A | Project Proposal | (none) | 2 | 2017-11-29 | 2017-12-01
B | 2 parameter VR graphing program | A | 2 | 2017-12-15 | -
C | Dissertation (Introduction and background) | A | 2 | 2018-02-08 | -
D | Back end multiparamter DSE illustartion program | B | 3 | 2018-02-15 | -
E | Dissertation (Project Tasks and reasoning) | A | 2 | 2018-02-23 | -
F | Multiparameter DSE illustration VR program | D | 4 | 2018-03-16 | -
G | Motion control support | F | 2 | 2018-04-01 | -
H | Dissertation (Results and evaluation | G | 2 | 2018-04-15 | -
I | Poster | F | 2 | 2018-04-17 | 2018-04-20
J | Dissertation (Conclusions and appendex) | C,E,H | 1 | 2018-04-23 | -
K | Dissertation final checks and proofing | J | 1 | 2018-05-01 | 04/05/2018 (final dissertation)
L | Demonstration | K | 2 | (rehearsal) 08/05/18 | 2018-04-10